## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
ahPPC9J_iEWFP8ESV1K3LpYAGu3k | Templates for DP DA | Backlog | Not started | Medium | Kay, Stephen | Kay, Stephen | 21/02/2022 |  | 11/03/2022 | false |  |  | Create the templates for materials to be submitted to the DP DA
gYoSL0tExkSaojWzZ_bueJYALOj9 | Slides with as-is BCF with scoring headlines & objective - see notes in book | In Progress | In progress | Medium | Maxted, Suzanne | Maxted, Suzanne | 17/02/2022 |  | 22/02/2022 | false
9-h4rNnCC06jIwI8KxIXuZYAPYsx | Review ToR comments | In Progress | Not started | Medium | Kay, Stephen | Kay, Stephen | 17/02/2022 |  | 17/02/2022 | true
r6EysRAxCkWN2S5VIqdZbJYAJK_M | Review DP DA ToR | For Review | In progress | Important | Cant, Caron;Gupta, Himani;Haigh, Claire;Hughes, Lottie;Struthers, Dorothy;Maxted, Suzanne;Yelland, John;Hood, Edward | Kay, Stephen | 14/02/2022 |  | 18/02/2022 | true |  |  | Please review the DP DA ToR and tick your name off when finished. Leave comments in the document directly | 6/10 | Edd;Christine ;Dot;Himani;John;Claire;Caron;Lottie;Andrew;Suzanne | DP DA
Enq2mQ2Rn0qm4xYM2W5xSZYAN4tZ | Create Business Rhythm | In Progress | In progress | Medium | Yelland, John | Yelland, John | 14/02/2022 |  |  | false
Oj4QBUFGDU6yonQlKDHdBpYACB77 | Develop domain model for product, bulletin, article & ? | In Progress | In progress | Medium | Maxted, Suzanne | Maxted, Suzanne | 10/02/2022 |  | 03/03/2022 | false |  |  |  | 0/2 | book time with content G7;develop domain model
9ngWVIAZ0ky6uBPGph2osZYAA1za | Define top level Processes | TBD | Not started | Medium | Yelland, John | Yelland, John | 10/02/2022 |  |  | false |  |  |  | 0/2 | Create Process Maps associated with top level processes;Define Top Level Processes
83pPyY7E10ygjRGrN8c3WpYAFbNJ | Confluence | Backlog | In progress | Medium | Maxted, Suzanne;Munday, Christine;Kay, Stephen | Kay, Stephen | 10/02/2022 |  | 25/02/2022 | false |  |  | Publish artefacts to Confluence pages: https://collaborate2.ons.gov.uk/confluence/display/DIGPUB/DP+Service+Design+Team | 3/5 | Publish architecture artefacts from Sparx into pages;CM to request joining access for Lottie and John. ;Link artefacts to existing items within Confluence (and outside);Request a page with access;Create structure
ElYfBBKXbE-22y1qTRRQ95YAKsL- | Milestone 1 | TBD | Not started | Medium |  | Hood, Edward | 09/02/2022 | 09/02/2022 | 23/02/2022 | false | [5 empty] | Milestone
TlBekBCz5Eqn8eClaQ59tpYAHPaz | Process map Digital Publishing | In Progress | In progress | Medium | Yelland, John | Yelland, John | 09/02/2022 |  |  | false
pBy4T--v3U-XHNgeYJ_JnJYAL2AO | Risk Assessment for product teams | In Progress | In progress | Medium | Haigh, Claire;Kay, Stephen | Kay, Stephen | 09/02/2022 |  | 25/02/2022 | false |  |  | Edd has asked us to perform informal risk assessments on each product team - primarily regarding the technical risk areas | 0/7 | Kapow (Find Census) - Gracie Lewis (meeting scheduled 17/02);Set up Intro chats with each of the areas to discuss further;Data Visualisations - Rob Fry / Ahmad Barclay;Team B (Get Data) - Fran Moore (meeting scheduled 17/02);Runtime Terror (Publishing Service) - {Paul Flynn);Find Insights - Gus Laios;Team 404 (Geography) - James Anderson (update sought via email) | RISK
oHhRvBbhzUq90EQ0LtLZdZYAFUhu | Slides for reasons for Website uplift | For Review | In progress | Medium | Hood, Edward;Kay, Stephen | Kay, Stephen | 09/02/2022 |  | 11/02/2022 | true
xQ4FkMfWkUOHpQ5558vrGZYAMIGc | Culture change | In Progress | In progress | Medium | Struthers, Dorothy | Hughes, Lottie | 07/02/2022 |  |  | false |  |  | Ongoing as it supports everything else | 3/5 | Analyse opinion survey;Design Directors Survey ;SMT workshop on culture;Establish culture pillar;Analyse G6/G7 survey results
mxfW3rtIHUysqpRIsxVgipYAPm7b | Change Strategy | In Progress | In progress | Medium | Struthers, Dorothy | Hughes, Lottie | 07/02/2022 |  | 28/02/2022 | false |  |  |  | 0/8 | Signpost SMT to Union and Shadow Board involvement ;Assess change capability;Change impact assessment;Readiness checks;Establish change structure;Refresh/Recruit new members to Shadow Board;Present the Coach network to Shadow Board;Set up a session with Shadow Board re Vision work
Cl5VlRbz5EG3zsNqvPkpLJYADQt5 | Set up backlog correctly | In Progress | In progress | Important | Cant, Caron;Haigh, Claire;Hughes, Lottie;Member;Maxted, Suzanne;Yelland, John;Hood, Edward;Munday, Christine;Kay, Stephen | Gupta, Himani | 04/02/2022 |  | 04/02/2022 | true |  |  | 1. Set up tasks as per guidelines on the Wiki (link below) 2. For all cards: - ensure both Bucket and Progress are set correctly - set due dates - add enough detail to be understood and check "Show on card" checkbox 3. Every day: - see what needs to be picked up from the backlog based on due dates and importance Link to Wiki: https://teams.microsoft.com/l/entity/com.microsoft.teamspace.tab.wiki/tab::4e6fd8a0-60af-4144-8561-5b6969f3b356?context=%7B%22subEntityId%22%3A%22%7B%5C%22pageId%5C%22%3A5%2C%5C%22sectionId%5C%22%3A12%2C%5C%22origin%5C%22%3A2%7D%22%2C%22channelId%22%3A%2219%3AUqNj-SupqaUM7qyDjQv_MU1kqvJOrTOLYmsfJAcxJVU1%40thread.tacv2%22%7D&tenantId=078807bf-ce82-4688-bce0-0d811684dc46 | 8/9 | Lottie Hughes;John Yelland;Claire Haigh;Edward Hood;Steve Kay;Christine Munday;Andrew Gibson;Caron Cant;Suzanne Maxted
jqhVe0nQ40yDgu11EZXVB5YAMbJJ | Get more context on IDS-D | In Progress | In progress | Medium | Gupta, Himani;Hood, Edward | Gupta, Himani | 04/02/2022 |  | 28/02/2022 | false |  |  |  | 1/2 | Whiteboard session to clearly understand vision/strategy of IDS-D and integration with rest of DP;Explore integration options in the org design
l4i66-xg30WSo7SvH7TxY5YAIOq6 | Project support | In Progress | In progress | Important | Hughes, Lottie | Gupta, Himani | 04/02/2022 |  | 18/02/2022 | true |  |  |  | 2/9 | Create Teams Executive Decision Log (for SMT access) - once format agreed with Edd by 07/02;Book in vision workshop part 2;Agree agenda with Edd and Himani in advance;Schedule recurring 3 week playbacks with the SMT by 07/02;Look at a way to produce project plan from backlog items;Logistics for SMT away day;Create Key Events Calendar - share draft with Edd and agree format on Teams by 07/02;Next playback to be run by Feb end;Update following the planning sessions
Agu6zRGTFEOO0qGTUL1NDJYAEYnK | Develop Program Steering Board | In Progress | In progress | Important | Gupta, Himani | Gupta, Himani | 04/02/2022 |  | 18/02/2022 | true |  |  |  | 2/5 | Agree agenda in advance;Schedule recurring meetings (arrange once Liz agrees proposed governance);SMT Steering Board (fortnightly) - agree proposal with Edd by 10/02;Put a structure and share with Edd;Run the session
ctp1j6RkEkSZNfS_kJsNBpYAJyId | Look at BASE Review | Backlog | Not started | Medium | Gupta, Himani;Hood, Edward | Gupta, Himani | 04/02/2022 |  | 28/02/2022 | false |  |  |  | 0/3 | Understand risk, dependencies if any;Understand their plan and timeline;Assess impact on DP interactions with rest of the ONS
iaTQJFz0kUeJyGLPrX9pmpYAGSBo | Feb Shadow Board | Backlog | Not started | Medium | Gupta, Himani;Hood, Edward | Gupta, Himani | 04/02/2022 |  | 20/02/2022 | true |  |  |  | 0/3 | Draft agenda ;Run the session by month end;Agree with SMT what can be shared with their teams on this transformation
914ET7k-DEyfyIDpHCtlR5YACSsX | Assess business view of content management/publishing process | In Progress | In progress | Important | Gupta, Himani;Hood, Edward | Gupta, Himani | 03/02/2022 |  | 28/02/2022 | false |  |  |  | 1/3 | Summarise observations;Engagement with Statistical Outputs areas ;Review content shared by RF on 03/02 on their business engagement (PICI)
H5N4Gk_bCk-UpTY5bigwHZYALGoX | Process Vision workshop outputs | In Progress | In progress | Medium | Cant, Caron;Gupta, Himani | Gupta, Himani | 03/02/2022 |  | 07/02/2022 | true |  |  | Go through Miro board and group subjects - plan 2nd workshop | 4/8 | Iterate with Edd;Group subjects on Miro into themes;Content for second workshop;Plan second workshop;Create Structure ;Set review meeting with Himani, Edd and Dot (thurs 17th);Plan culture workshop with Dot;Plan away day workshop with Dot
j6ycbYhvaEC_1dslg-200pYAEha- | Director Survey Questions | In Progress | In progress | Medium | Gupta, Himani;Struthers, Dorothy;Munday, Christine | Gupta, Himani | 03/02/2022 |  | 18/02/2022 | true |  |  |  | 2/3 | Review and agree questionnaire with Edd and Liz;Christine and Dot to refine/edit into a questionnaire;Himani to provide an outline of questions from previous work that has been done
f633oS_5L0WvVV1QPuUN7JYANdQv | Tech lead discovery | Backlog | Not started | Important | Gibson, Andrew | Gibson, Andrew | 03/02/2022 | 30/01/2022 | 17/02/2022 | true |  |  |  | 0/3 | Document processes according to James A;Document processes according to Eleanor;Document processes according to Gedge
PdcGaG0Ch0qw1SSVDGnFgJYAH-EX | Meetings policy - quick wins | Backlog | Not started | Urgent | Gibson, Andrew | Gibson, Andrew | 03/02/2022 |  | 11/02/2022 | true |  |  |  | 0/3 | Suggest to Liz and Edd in connection with survey in development, change plan;Agree delivery plan;Design quick wins ToR beta
DsdRAF0OSkW-0vaWutIWtJYAOSQk | Paul Flynn looking at where we store documentation | TBD | Not started | Medium |  | Hood, Edward | 01/02/2022 |  |  | false
nZAsM8TPhUmqxGzYyx9SiJYACyIT | Replay team embedding reports (1) | In Progress | Not started | Important | Gibson, Andrew | Gibson, Andrew | 01/02/2022 |  | 17/02/2022 | true
P_v5FeKZw0yyZU1C5YsYk5YACN0P | Review Risks | Backlog | Not started | Medium | Gupta, Himani;Hughes, Lottie | Hughes, Lottie | 01/02/2022 |  | 18/02/2022 | true
wDhquP96gkqvS15OkzwsS5YAKqrg | Complete Hut Six Training | In Progress | Not started | Urgent | Cant, Caron;Gupta, Himani;Gibson, Andrew;Hughes, Lottie;Member;Yelland, John | Hood, Edward | 01/02/2022 | 31/01/2022 | 28/02/2022 | false |  |  | All those with ONS laptops must complete hut Six Training, otherwise access will be revoked. You should have received and email detailing how to complete the training. | 4/10 | Steve;Suzanne;Edward;Andrew;Andrea;Lottie;John;Himani;Caron;Christine
DUNPVOuYskm5vEsBjyAaipYAF78- | Playback Artifacts | Backlog | Not started | Medium | Kay, Stephen | Hood, Edward | 01/02/2022 |  | 25/02/2022 | false |  |  | Steve; can we book some time to take me, and maybe other in the team through the Architecture diagrams we have created please.
fyHiFjbRUkq2bWO37oQr9pYAIkO3 | refine wording in discovery report | Backlog | Not started | Medium |  | Maxted, Suzanne | 31/01/2022 |  |  | false |  |  | e.g. Suzanne had a few words to adjust - nothing major
rH7hxNnnxki0P3rsFYiJ25YAJcRP | strategy/capability view BMM | Backlog | Not started | Medium | Maxted, Suzanne | Maxted, Suzanne | 31/01/2022 |  | 24/03/2022 | false |  |  | Awaiting time with Edd | 3/5 | develop view;book time with Edd;put TO-BE capabilities on a slide as input for Dot;agree benefit or a strategy/capability BMM view according to Edd's preference;liaise with Caron / Dot on vision strategy input
XjsHWiFAo0uS4mHeuAW6CZYADYjO | Pick up with Steve Vickers around opportunities and reporting | TBD | Not started | Medium | Kay, Stephen | Hughes, Lottie | 31/01/2022 |  |  | false
gHS66qi8S02PRpwd3DwDLJYAOaGS | Strategy Gaps | For Review | In progress | Important | Gupta, Himani;Struthers, Dorothy;Hood, Edward;Kay, Stephen | Kay, Stephen | 31/01/2022 |  | 11/03/2022 | false |  |  | Identify the strategies that need creating and prioritise them | 3/4 | Identify;revise from feedback;Prioritise;Get feedback from Tech leads
GDgh_1GqmEajQvCrSK1yOZYAOQjF | Look into Head of Professions, DST org structure & DDAT hub | Backlog | Not started | Low | Gupta, Himani | Hughes, Lottie | 31/01/2022 |  |  | false
cpSTTU8cKUy6oCbsCRJI15YAEFMi | Look at maturity of service management in systems & tech | TBD | Not started | Medium | Member;Kay, Stephen | Hughes, Lottie | 31/01/2022 |  |  | false
YAwcow0GmEaQgRX02SPWxZYAJLW1 | Look at BCP plan on sharepoint | In Progress | In progress | Medium | Member | Hughes, Lottie | 31/01/2022 |  |  | false |  |  | Review document to see if there are any gaps
LjIx0yLRz0SMo3-yP72C15YAI37V | Add DP resourcing board to governance boards and speak to Jade Kelly | TBD | Not started | Medium | Hughes, Lottie;Member | Hughes, Lottie | 31/01/2022 |  |  | false
9E7cPsixUkqDgImuzSY43pYADXBW | Validate value network map | In Progress | In progress | Medium | Yelland, John | Hughes, Lottie | 31/01/2022 |  |  | false
d17nGOFQVUaHdD9pUJVdy5YAD-JU | Knowledge management plan | Backlog | In progress | Medium | Member | Hughes, Lottie | 31/01/2022 |  |  | false |  |  | Producing a deck for a high level Knowledge Management plan https://officenationalstatistics.sharepoint.com/:p:/s/CDP_Service_Design_Team/ESEyTKT0YvhFph7VsVRjVxIBm-QkXtNuYbaGnbX6EYy1Mg?e=yoTMNQ
ToPztof8KkKzR85Evl3QZ5YAOu9f | SDT Team Risk | In Progress | Not started | Medium | Haigh, Claire;Hughes, Lottie | Hood, Edward | 01/02/2022 |  | 04/02/2022 | true |  |  | Clarie; would you mind working with Lottie to workshop teams risks. I am keen that we are identifying, managing and reporting this in a better practice way.
JW18eRjsdUCpRWpCNEjkGJYAMLR3 | Validate Org charts | In Progress | In progress | Medium | Hughes, Lottie;Yelland, John | Hughes, Lottie | 31/01/2022 |  | 08/02/2022 | true |  |  |  | 2/2 | Build process to maintain with Business Support;Checked by G6s
85kZYpL8YUWvnkibYH1fDJYACRbT | As Is Ops Model | In Progress | In progress | Medium | Member | Member | 27/01/2022 |  | 11/02/2022 | true
Fo_iV1QCjEKRUFOXemaILpYAAPXF | Define Service Offerings | In Progress | In progress | Medium | Member | Member | 27/01/2022 |  | 25/02/2022 | false |  |  | Reviewing recorded interviews to detail services
jV3lNsw63UiZvF_EZ1B7fZYANpFz | Develop support materials for design phase | In Progress | In progress | Medium | Cant, Caron | Cant, Caron | 27/01/2022 |  |  | false |  |  | Develop a suite of support packages to offer to teams to give them support (identified in the disco work as gaps in provision) | 1/3 | Identify common themes for support;check across healthheck attendes for feedback;Create support mterials
HNantS71yU-m9oSXrgeE8pYAHbGO | Review of Isights materials/team engagement | In Progress | Not started | Medium | Cant, Caron | Cant, Caron | 27/01/2022 |  |  | false |  |  | Engage with Andrew to determine engagement to date and to go through the report to date. | 0/3 | Align common themes/support;Go through activity to date;Set up session with Andrew
D3rLr4OG9ky0HU89Y5WDlpYAKIEE | Prep for Vision workshop | In Progress | In progress | Medium |  | Gupta, Himani | 27/01/2022 |  | 31/01/2022 | true |  |  | Developing Miro board and presentation for workshop to determine vison. | 7/8 | Create Miro board for interactive exercises;2 mins for each person in session (what they want to achieve);Review documentation (strategies) to input to where we are now;Add a couple of bullets to session invite (what do you want to get out of transformation, what will ;Add behaviors in leadership team session set up (be more blue0;Draft email (agenda and points above);Look at the strategy Darren shared;Develop slides
B9qOyeobd0mlih3RJXRO3JYAJ3Qd | Agree key decisions/design principles with SMT | In Progress | In progress | Important | Gupta, Himani;Hood, Edward | Gupta, Himani | 27/01/2022 |  | 28/02/2022 | false |  |  |  | 0/4 | Refine based on Playback feedback and share with Edd;Agree in smaller groups - test with DW/RF ;Agree with Liz (email) ;Agree with rest of SMT (email)
NzYj74b2MEOmS5oR3cut8pYAMppy | Working with CDP Business Support on new DP Home Page/folder design | In Progress | In progress | Medium | Munday, Christine | Munday, Christine | 26/01/2022 | 27/01/2022 | 22/02/2022 | false |  |  | Working with a team on this linked to Samantha Busby from CDP_BusinessSupport | 3/3 | Meeting being set up with KIM next and Business Support, Sam Busby leading but will loop me in. ;Sent survey results to Business Support DP - about Home Page feedback. ;Harry Tilley in Internal Comms has had training on Microsoft 365 capabilities - will request slides
ey7qqkVzj0SCh4XBdacgsJYAPusF | Comms, Culture and Change tasks - broken down and progressing through | In Progress | In progress | Medium | Munday, Christine | Munday, Christine | 26/01/2022 | 26/01/2022 | 24/02/2022 | false |  |  | Working through tasks listed. | 12/20 | Set up a SharePoint area - Podcasts/videos - Culture, Change and Comms ;Design a charter on how blogs should be checked for governance ;Audit communication platforms and emails - where do they go for communications? Ask Sue, Taha etc;See if we can write a piece for Reggie intranet for the programme - what are we trying to achieve in;Understand what the survey form needs to look like for the wider ONS Directors (will this include De;Review the online form results for Grade 6 and Grade 7;Review key themes of Miro board ;Create engagement resources;Dot to attend meeting with business support and KIM on 04/02 with me to review how to improve DP SP;SMT - Workshop on Change Management - More of a check-in and do they feel able to lead it. Strengths;Pros and Cons of using slack - some risks already raised. ;Tie in an FAQ. ;Strengthening service - DP - As a service - what can we provide?;Meeting Dorothy on 02/02 to have introductions and seek assistance from one another to expedite ;Raise awareness of the programme on ADKAR;List of key Pillar people to add in - Coaches / Champions for a DP Pillar ;Review SharePoint Champion feedback and share with Dot ;Review Shadow Board attendees. Come up with Terms of Reference - apply meaning to it. ;Tie in list of resources;Design a newsletter for DP Service Design updates for email/slack
5bUPde7Vf0K9SsKm98ITZJYAMjLG | Initial contact with Darren Barnes / IDS | In Progress | Not started | Important | Gibson, Andrew | Gibson, Andrew | 26/01/2022 |  | 11/02/2022 | true |  |  | Make first contact with Darren Barnes IDS (Content) and Darren Waters (Content Teams) to make plans to deep dive into issues. | 2/4 | Initial contact;Identify embedding target;Attend G6/7 meeting;Draw out team structure
_5HKiw-T-0m60gSpfivw_5YAKrI9 | Team B - Get Data embedding | In Progress | In progress | Urgent | Gibson, Andrew | Gibson, Andrew | 26/01/2022 |  |  | false |  |  |  | 7/12 | PO initial comms;Report prep;Report finalisation;Access and agreement of wow;Delivery task 2;Delivery task 3;Onboarding;TL initial comms;Tentative scoring;Delivery task 1;Agile ceremonies overview;Report on Team working / autonomy / guilds
UcXw7NytfEGTne5mXlK6YpYAAkfo | Discovery work on Social Media | In Progress | In progress | Medium | Yelland, John | Yelland, John | 26/01/2022 |  |  | false
V3XvofIV70eS149MF5KzuJYAK1Zt | Meetings policy - survey | Backlog | In progress | Important | Gibson, Andrew | Gibson, Andrew | 26/01/2022 | 01/02/2022 | 25/02/2022 | false |  |  |  | 2/7 | Pass to Liz (who has asked for visibility);Initial overview with JA (internal DP);Communicate with Edd determine schedule;Build survey;Follow up and collate;Dispatch;Communicate findings
xpp_6dYkNka2fNK3TRgkQZYAHt8t | Migrate relevant docs to ONS Teams | Backlog | Not started | Medium | Hughes, Lottie | Gupta, Himani | 24/01/2022 |  | 02/02/2022 | true
Hulh0tP5-kWuEnHYeDH2wpYACAOJ | Org design workshop prep | In Progress | In progress | Medium | Gupta, Himani | Gupta, Himani | 24/01/2022 |  | 28/02/2022 | false |  |  |  | 1/4 | Testing with smaller groups - DW/RF;Review of initial thinking with Liz (10/12);Whiteboarding on 09/02 and 10/02 with Edd to incorporate SMT feedback from Playback;Conduct workshop with SMT on Away day (02-03 Mar)
K1a9Mp1iiE6O6Hvy2n-kHJYAI4an | Develop to-be business capability | In Progress | In progress | Medium | Maxted, Suzanne | Maxted, Suzanne | 24/01/2022 |  | 28/02/2022 | false |  |  | eg Content Enrichment vs Data Journalism, Data Curation with DP? (after strategy wshop). See emailed notes to self 03/02/2022 attached. See attached results of scoring. See IDS model attached. | 2/6 | develop TO-BE BCF - see email notes & attachments;book/time with Edd/Himani to look at draft TO-BE;liaise with Charlotte Hirst's team on ONS BCF development - ongoing;book time with Edd/Himani to playback scoring - just the headlines;update register with descriptions of levels we use;update register with to-be level 2 descriptions
_4GPkoj9P0utbXhpou9X55YAKdGN | Create Delivery diagrams | For Review | In progress | Medium | Kay, Stephen | Kay, Stephen | 18/01/2022 |  | 11/02/2022 | true |  |  | Diagram how the product teams deliver their artefacts - as this is common across teams, a single diagram is sufficient
vl0i2oCRlUqVkaiVPBMm1JYAEy82 | Static Files | In Progress | In progress | Medium |  | Hood, Edward | 07/11/2021 |  |  | false |  |  | Caron and Himani Working on this.
7_65dS2q1EyNk4yHbSfGOpYABMGf | Chartbuilder | In Progress | In progress | Medium |  | Hood, Edward | 07/11/2021 |  |  | false |  |  | Caron and Himani Working on this.
YiVmQxeWjUKwAP4ptbxYopYADxqW | Summarise G6/ G7 survey responses | In Progress | Completed | Medium | Munday, Christine | Hughes, Lottie | 27/01/2022 |  | 14/02/2022 | false | 16/02/2022 | Munday, Christine | Draft summary has been produced, and an Exec summary is in creation. Duplicated this card in the planner, so have removed the other card**
TLplPZQSGk26yj2e-4uTQJYAMEZC | Darren and Rob Deep Dive | Done | Completed | Medium | Gupta, Himani | Hood, Edward | 01/02/2022 |  | 09/02/2022 | false | 16/02/2022 | Gupta, Himani | Agree to work with Rob and Darren to make sure the Disco Report Reflects their area better. | 3/3 | Gather Data Points;Document summary findings for playback;Playback to DW/RF - rescheduled to 09/02
WjuBdTWT4EW7OcDmyaPypZYACPjE | Architecture Artifact Map | Done | Completed | Important | Maxted, Suzanne;Kay, Stephen | Kay, Stephen | 02/02/2022 |  | 11/02/2022 | false | 15/02/2022 | Kay, Stephen | List the artifacts that have been produced and highlight the ones that will be produced. Fine except remove benefits map - SJM | 2/2 | Suzanne's Artifacts;Steve's Artifacts
RICzkJS5L0GOICgMETi60JYAOSRL | Division AFOs | Done | Completed | Medium | Yelland, John | Gupta, Himani | 03/02/2022 |  | 10/02/2022 | false | 14/02/2022 | Yelland, John |  | 3/3 | First look at Airtable - Edd/Himani with Content team on 03/02;Playback to Edd and Himani;John to explore 'art of possible' and talk to Elizabeth
p9jqwVwNpk-kcBMLko1a6ZYAOJwT | Walkthrough session with James and Paul | In Progress | Completed | Medium | Cant, Caron | Gupta, Himani | 04/02/2022 |  | 08/02/2022 | false | 14/02/2022 | Cant, Caron | Invitation sent Friday 4th Feb | 0/1 | Walkthrough of vision board as agreed with the SMT
NGOH0kXJLUSsO7r6Gp10E5YAFLVK | Summarise G6/G7 responses into a PPT | Backlog | Completed | Medium | Munday, Christine | Munday, Christine | 10/02/2022 |  | 11/02/2022 | false | 11/02/2022 | Munday, Christine
hvKhmS5cXUm3pkI6--jDpJYAKxUy | Update project plan | Done | Completed | Medium | Hughes, Lottie | Hughes, Lottie | 27/01/2022 |  | 09/02/2022 | false | 11/02/2022 | Hughes, Lottie | To be combined with task of putting together a key events calendar on teams site etc
DOchLxBFPkmlPh7de0oU0ZYAMixO | Complete problem context diagram with data | Backlog | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 02/02/2022 |  | 10/02/2022 | false | 10/02/2022 | Maxted, Suzanne
XubLb_tCDU-B75VpIzgB55YANtdS | complete & review benefit mapping template | Backlog | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 24/01/2022 |  | 10/02/2022 | false | 07/02/2022 | Maxted, Suzanne | Includes example one line of sight. Awaiting discussion with Edd on 10/2
r-lttIOt6kWvCEeMSdbqH5YACHRf | Strategy session | Backlog | Completed | Medium | Cant, Caron | Cant, Caron | 27/01/2022 |  |  | false | 07/02/2022 | Cant, Caron | Set a session for Edd/Caron to discuss strategy meeting attended last week
ewzSOnmqfkeaBUSqS74a3ZYAPa2d | Schedule SMT sessions | Done | Completed | Medium | Gupta, Himani;Hughes, Lottie | Gupta, Himani | 24/01/2022 |  | 04/02/2022 | false | 07/02/2022 | Hughes, Lottie | Confirm provisional date for SMT away day Duplicated task
c0SIMrE_pkOXlPGZHBsBDZYAE0vl | Continue to collect Gov ToR's for John | Done | Completed | Medium | Yelland, John;Munday, Christine | Munday, Christine | 26/01/2022 |  | 04/02/2022 | false | 04/02/2022 | Yelland, John
b8tPcNK3_0S1OT5JBSL2EJYAONWp | Check if DST manage SSL cert expiring and check if DP apps are on CMDB | Done | Completed | Medium | Kay, Stephen | Hughes, Lottie | 31/01/2022 |  |  | false | 04/02/2022 | Kay, Stephen | These are important factors to know when formulating a strategy as people need to know where they should go for certificates, how they are told when they expire, what to do when they do, etc. Plus they need to know where to register their product within the CMDB (if it exists) | 2/2 | CMDB;SSL management
evsNzWy3lUCkG6wQE99KFpYAHAjz | Onboarding Dot to project | Done | Completed | Medium | Gupta, Himani | Gupta, Himani | 04/02/2022 |  | 04/02/2022 | false | 04/02/2022 | Gupta, Himani
WeEUv51qzku9SoR98SR6S5YABNBk | Shadow Board - 03/02 @1400 | Done | Completed | Medium | Gupta, Himani;Hood, Edward | Hood, Edward | 31/01/2022 |  | 03/02/2022 | false | 04/02/2022 | Gupta, Himani | Shadow Board is on the 03/02 @ 1400. Need Agenda. Will cover EOS | 4/4 | Agree Agenda;Agree Faclitator ;Produce Content;Run Session
dc3aUxLKVkGSh8irKj124ZYANsTB | Review all governance meeting terms of reference on sharpoint | Done | Completed | Medium | Yelland, John | Yelland, John | 26/01/2022 |  |  | false | 03/02/2022 | Yelland, John
iqXZeA7PLEWky5MMpExMIJYAD0kv | Draft Technical Maturity Assessment | Done | Completed | Medium | Kay, Stephen | Kay, Stephen | 03/12/2021 |  | 23/12/2021 | false | 03/02/2022 | Kay, Stephen | Process for determining the maturity of the current technical landscape | 5/5 | Sent out capture form;Populate Sparx diagrams;Chase responses;Draw inferences;Analyse responses
rbetpEwttEa7pnVWPmme35YAH_B8 | Hut6 Training | Done | Completed | Medium | Kay, Stephen | Kay, Stephen | 28/01/2022 |  | 28/01/2022 | false | 03/02/2022 | Kay, Stephen
yzCsIkpuCUiER83QeX5eRpYAMBjC | Build TOR for TDA | Done | Completed | Medium | Kay, Stephen | Hood, Edward | 07/11/2021 |  |  | false | 03/02/2022 | Kay, Stephen
wv0N-5oMo0mw1CylBqGGVJYAGOjm | AFOs for G6 level | Done | Completed | Medium | Gupta, Himani;Hood, Edward | Hughes, Lottie | 31/01/2022 |  |  | false | 03/02/2022 | Hood, Edward
LRy9X2jEJEecakeu4cHAx5YAATIs | Review Kapow survey response | Done | Completed | Medium | Kay, Stephen | Kay, Stephen | 26/01/2022 |  | 04/02/2022 | false | 02/02/2022 | Kay, Stephen | Reviewed - very similar scoring to Team 404 (slightly higher)
I_Uz-2m700Sm_0pm0f0KYZYAEYrJ | Prepare & run workshop for BCF to collect maturity scoring, gaps/improvements in capability | In Progress | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 31/01/2022 |  | 02/02/2022 | false | 02/02/2022 | Maxted, Suzanne
kHFnIOlnD0CU9fvDxt1Yc5YABT8P | Gather and add data for problem context | In Progress | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 02/02/2022 |  | 01/02/2022 | false | 02/02/2022 | Maxted, Suzanne
vplDqfdT20WBKdqMNydu-pYAOGXr | Update RID/ Action log | Backlog | Completed | Medium | Hughes, Lottie | Gupta, Himani | 24/01/2022 |  | 31/01/2022 | false | 02/02/2022 | Hughes, Lottie
juqJnWTdgUG6dXEHLZQsOpYAFvrI | Provide Extention Costs | Done | Completed | Medium | Gupta, Himani | Hood, Edward | 01/02/2022 |  |  | false | 01/02/2022 | Hood, Edward
C1EkmNoggE6rJSoeT3IcSJYAH6OG | As-is BCF validated and documented with SMT | TBD | Completed | Medium | Maxted, Suzanne | Hughes, Lottie | 01/02/2022 |  |  | false | 01/02/2022 | Maxted, Suzanne
dUn3edjJ7kCg2YofBc8V5ZYAJ4JF | Holding task here - re: article for Reggie needs sign off | Done | Completed | Medium | Munday, Christine | Munday, Christine | 26/01/2022 | 13/01/2022 | 03/02/2022 | false | 31/01/2022 | Munday, Christine | Article has been signed off for Reggie on three separate occasions. Task to be held on board for time-being. | 3/3 | Item was held back from Liz and pulled from Reggie 27/01/22 - messaging to be reviewed. ;Preview passed to Liz by 9pm. Edits made. Should be on Reggie tomorrow. 26/01/22;Awaiting final sign off from Liz.
Ew0sCbw-pE28hIxXOT-4AJYADL-F | Document definitions of business capability | Backlog | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 31/01/2022 |  |  | false | 31/01/2022 | Maxted, Suzanne
-P6jK0W_8kSNrCwGtXGjSpYAL8k5 | Create an FAQ - WIP - for Programme to clarify questions and answers | Backlog | Completed | Medium | Munday, Christine | Munday, Christine | 26/01/2022 |  | 03/02/2022 | false | 31/01/2022 | Munday, Christine
SGbHnG1BTEW4wQviZsW-9ZYAICwf | Document definitions of service, service offerings, service catalogue, support model, capability etc | Backlog | Completed | Medium | Member | Hughes, Lottie | 27/01/2022 |  | 27/01/2022 | false | 27/01/2022 | Member | This has been added to Teams https://officenationalstatistics.sharepoint.com/:w:/s/CDP_Service_Design_Team/EZ4SDqWIuFlBkEXL3BUojBUBqx1Va60FLhimnHOg_ESChA?e=wypuDE
X6e96UK_g0yOymQhyo0xLpYAPPk5 | Compile results from SharePoint survey | Done | Completed | Medium | Munday, Christine | Munday, Christine | 26/01/2022 |  | 27/01/2022 | false | 27/01/2022 | Munday, Christine
SPr-sLz5G06XDvxmnT9Wf5YAPcyu | Contact Service Design Graphic designer RE: Risk strategy graphic tool | Done | Completed | Medium | Haigh, Claire;Munday, Christine | Munday, Christine | 26/01/2022 |  | 31/01/2022 | false | 27/01/2022 | Munday, Christine | Contacted James Peace in TISS Service Design - for design tool to use 26/01 / dependent on result will ask Mel McKeown for tool.
nbYmtKUIBkuK6ZxuG-foupYAMOeK | Discovery Playback follow up | Done | Completed | Medium | Gupta, Himani | Gupta, Himani | 25/01/2022 |  | 27/01/2022 | false | 27/01/2022 | Gupta, Himani
xL62pSQhxUa2wwWxOU_S1pYAGy9T | DP survey follow up | Done | Completed | Medium | Hughes, Lottie;Munday, Christine | Gupta, Himani | 26/01/2022 |  | 26/01/2022 | false | 26/01/2022 | Munday, Christine
aZ8GlYEAIUGmwy-XVtUF95YAH7a6 | Meet with Lottie to gain Miro access for Org chart - review for Stakeholder map | Done | Completed | Medium | Hughes, Lottie;Munday, Christine | Munday, Christine | 26/01/2022 |  | 26/01/2022 | false | 26/01/2022 | Munday, Christine
GXr-1VpBJ0O4ZQkZFsYp5pYAIIR6 | Discovery Playback | Done | Completed | Medium |  | Gupta, Himani | 24/01/2022 |  | 25/01/2022 | false | 25/01/2022 | Gupta, Himani
bZBIBmU0e0eRHqzLzz6zGZYAJsKy | Discovery Report | Done | Completed | Medium | Gupta, Himani;Hughes, Lottie | Gupta, Himani | 24/01/2022 |  | 24/01/2022 | false | 25/01/2022 | Gupta, Himani
St5RliDwI02uZnjYPMnhoZYABgoH | Develop a high level support capability model for census (that can align to longer term DP business capability framework) | In Progress | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 04/11/2021 |  |  | false | 07/12/2021 | Maxted, Suzanne
YRzbcPwe20K41CpLsS1h_JYAHRuc | Access Sparx and Kevin Tann's existing business capability estate | Done | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 04/11/2021 |  | 08/11/2021 | false | 03/12/2021 | Kay, Stephen | Requested access from Edd. In the meantime, requested estate artefacts from Kevin Tann and access to Miro boards from Nick Bailey. IT support awaiting approval from Rebecca Trickey
zQ59Sbp9VEO2a6JPFdc7hZYAEB9f | Complete and issue the model of the problem as explained to Suzanne | Done | Completed | Medium | Maxted, Suzanne | Maxted, Suzanne | 04/11/2021 |  |  | false | 08/11/2021 | Maxted, Suzanne

## Plan name
Plan name | Service Design Team Backlog
Plan ID | YVDEydJX3EipqQkRAFmzEZYAAZBk
Date of export | 22/02/2022